## October-5-Review
October 5, 2026 — Go / No-Go Decision Dashboard
Rule: the project continues in product-development mode if at least 2 of 3 metrics are PASS on October 5, 2026. Otherwise, activate support-mode plan.
# | Metric | Threshold (fill in) | Actual on Oct 5 | Status | How to measure / notes
1 | Monthly Recurring Revenue or monthly gross revenue | e.g. X USD |  |  | MRR or gross revenue for September 2026, average of last 3 months preferred. Owner: revenue zone.
2 | Retention (D30 or M1) | e.g. Y % |  |  | Cohort retention at day 30 (or month 1, pick one and keep it). Owner: product zone.
3 | Paid acquisition unit economics (LTV / CAC or payback) | e.g. LTV/CAC ≥ Z, or payback ≤ N months |  |  | Measured on paid channels only. Owner: growth zone.
| Passes (count): | 0
| Fails (count): | 0
| Decision: | REVIEW REQUIRED — fill in all statuses
Legend
Blue text = input cell (fill in)
Yellow fill = key assumption — needs a real number before the October review
Black text = formula
Note on C4: Fill thresholds on the next co-founder call. Keep them absolute numbers, not ranges. Use the ones everyone agrees to live by.

## Monthly-tracking
Monthly metrics tracking — April to October 2026
Fill in actuals each month. The last row is what gets copied to the October-5-Review sheet.
Month | MRR / Revenue ($) | Revenue MoM growth | D30 Retention (%) | Paying users | Paid spend ($) | Paid signups | CAC ($) | Notes
Apr 2026 | [6 empty] | 0
May 2026 |  | 0% |  |  |  |  | 0
Jun 2026 |  | 0% |  |  |  |  | 0
Jul 2026 |  | 0% |  |  |  |  | 0
Aug 2026 |  | 0% |  |  |  |  | 0
Sep 2026 |  | 0% |  |  |  |  | 0
Oct 2026 (as of Oct 5) |  | 0% |  |  |  |  | 0
Note: highlighted fill = key input. Keep methodology consistent across months (same retention cohort definition, same CAC scope).

## Support-mode-plan
Support-mode activation plan (contingency)
If at least 2 of 3 metrics FAIL on October 5, this plan activates. It describes how to wind down development and shift to a minimal-support revenue-extraction mode. Fill in specifics while heads are cool, not under stress.
# | Action | Owner / deadline
1 | Freeze new product development (announce internally) | [Owner __], within 7 days
2 | Document current product state and critical runbooks | [Owner __], within 14 days
3 | Reduce infrastructure cost to support-only baseline (target: $____ / month) | [Owner __], within 21 days
4 | Pause monthly base dividends, switch to cash-positive distribution only | [All], from next month
5 | Define minimum support SLA (bug fixes only, response within 48h on business days) | [Owner __], within 14 days
6 | Marketing: halt paid acquisition, keep SEO / organic only | [Owner __], within 7 days
7 | Quarterly cash review: decide keep-running vs. sell vs. sunset | [All], every 90 days